## Template Gantt
| Last Updated On: | 2024-07-16
[8 empty] | 2024 | [13 empty] | 2025
| Project Start Date: | 2024-07-02 | [5 empty] | 2024-07-15 |  |  | 2024-08-26 |  | 2024-09-23 |  | 2024-10-21 |  | 2024-11-18 |  | 2024-12-16 |  |  | 2025-01-27 |  | 2025-02-24 |  | 2025-03-24 |  | 2025-04-21 |  | 2025-05-19 |  | 2025-06-16 |  | 2025-07-14
| Project Name: | ENTER PROJECT NAME HERE |  |  |  |  | Week Starting: | 2024-07-01 | 2024-07-15 | 2024-07-29 | 2024-08-12 | 2024-08-26 | 2024-09-09 | 2024-09-23 | 2024-10-07 | 2024-10-21 | 2024-11-04 | 2024-11-18 | 2024-12-02 | 2024-12-16 | 2024-12-30 | 2025-01-13 | 2025-01-27 | 2025-02-10 | 2025-02-24 | 2025-03-10 | 2025-03-24 | 2025-04-07 | 2025-04-21 | 2025-05-05 | 2025-05-19 | 2025-06-02 | 2025-06-16 | 2025-06-30 | 2025-07-14
Milestone # | Task # | Activity | Start | End | Number of Working Days | Status | % Work Done
1 |  | Project Kickoff | 2024-07-02 | 2024-07-02 | 1 | Complete-G | 100% | bar: 2024-07-01
| 1.1 | Kickoff Meeting | 2024-07-02 | 2024-07-02 | 1 | Complete-G | 100% | bar: 2024-07-01
2 |  | Formulation | 2024-07-16 | 2024-12-03 | 101 | In Progress-O | 20% | bar: 2024-12-02
| 2.1 | PK Studies | 2024-07-16 | 2024-09-24 | 51 | In Progress-O | bar: 2024-09-23
| 2.2 | Non-GLP Efficacy Studies | 2024-09-10 | 2024-12-03 | 61 | Not Started-G | bar: 2024-12-02
3 |  | Milestone 3
| 3.1 | Task 1 | 2024-07-16 | 2024-08-12 | 20 | In Progress-O | bar: 2024-08-12
| 3.2 | Task 2 | 2024-07-16 | 2024-07-29 | 10 | In Progress-R | 10% | bar: 2024-07-29
| 3.3 | Task 3 | 2024-07-16 | 2024-08-12 | 20 | Not Started-R | 0% | bar: 2024-08-12
Status
In Progress-R
In Progress-O
Complete-G
Not Started-G
Not Started-R
Formulas:
Number of Working Days = IF([End]="","",NETWORKDAYS([Start],[End]))

## Key for Gantt
Key for Charts
Symbol | What it means
Anticipated date of milestone/task completion
Milestone/Task Complete
Milestone/Task has not started but is delayed and/or past anticipated end date
Milestone/Task is in progress but is delayed and/or past anticipated end date
In Progress-R | Milestone/task in progress and behind schedule (red)
In Progress-O | Milestone/task in progress and on-time (orange)
Complete-G | Milestone/task completed (green)
Not Started-G | Milestone/task not started and on-time (green)
Not Started-R | Milestone/task not started and behind schedule (red)
Number of Working Days | Number of Working Days to complete task based on anticipated Start and End Date
% Work Done | % of work done on Milestone or Task
Light blue bars indicate the Milestone/Task Timeline, with a Black Diamond as the anticipated date of Milestone/Task completion. Note if you list your Milestone/Task status as "In Progress-O" or "Not Started-G", the diamond will remain with a light blue background, as it is determined the Milestone/Task will be completed on the anticipated end date.
Dark blue bars represent the % work done. Once you insert the % Work Done on a Milestone/Task, the dark blue bars will appear on the gantt.
This is representative of a Milestone/Task that has been given the status "In Progress-R". There has been some work completed, given the dark blue bar, but the red diamond indicates that the Milestone/Task is delayed and/or past the anticipated end date.
This is representative of a Milestone/Task that has been given the status "Not Started-R". The bars are light blue, as no work has been started and the Milestone/Task completion date is projected to be delayed.